## FR
A
[16 empty] | DAILY DRILLING REPPORT | [8 empty] | N°: |  | 18 | [5 empty] | Date: |  |  | 10/01/2013
|  |  |  | Depth @ 24h : |  | 2839 | ft /TVD: | 2839 |  | ft | PROGRESS : | 89 |  | ft | in |  | 9.75 |  | h |  |  |  | Last Casing/ Liner : |  |  | 13"3/8 |  | 61# J55 BTC |  | AT: |  | 2746 |  | ft, | Top AT: |  |  |  |  | ft
DEVIATION
[35 empty] | Depth |  |  | incl |  | Azim. |  | TVD
[35 empty] | 2740 |  |  | 1˚
[35 empty] | PITS |  |  |  |  | Volumes (bbl)
[35 empty] | Active |  |  |  |  | 580
[35 empty] | Reserve |  |  |  |  | 724
Kill Mud
[35 empty] | Hole |  |  |  |  | 432
| TIMING |  | OPERATION DESCRIPTION | [8 empty] | CODE | Initial Depth (ft) |  |  |  | Final Depth (ft) |  |  | Company |  | Rate | [8 empty] | SERIAL | [6 empty] | HOURS
| 00:00 | 01:30 | Lay down WEATHERFOR Links, Lafleur & surface equipments | [8 empty] | DESP | [9 empty] | T1 | [8 empty] | 1762-5051 | [6 empty] | 116
| 01:30 | 03:00 | Pick up tester cup and test BOP, Hydril, Pipe Rams, Chock & Kill Lines @ 1000psi ok | [8 empty] | TBOP | [9 empty] | T2
| 03:00 | 06:00 | Pick up 5" DP and rack in the derrick ( 15 stands= 1400ft) | [8 empty] | GERB | [9 empty] | T1
| 06:00 | 07:00 | Lay down DC 9"1/2, Shock Sub and Stabilizer | [8 empty] | DGERB | [9 empty] | T1 | [6 empty] | BHA Components
| 07:00 | 13:00 | Pick up Used PDC Bit, DC 8", STB and RIH Drill String (Tag Top Plug) | [8 empty] | DGDC | 00 |  |  |  | 2661 |  |  |  |  | T1
| 13:00 | 14:15 | Drill out Top , Bottom plugs , float collar ,cement & float shoe. | [8 empty] | REFOR | 2661 |  |  |  | 2750 |  |  |  |  | T1 | [11 empty] | Jts |  |  | Len (ft) |  | I.D (in) |  | O.D (in)
| 14:15 | 24:00 | Drill 12"1/4 section | [8 empty] | FOR | 2750 |  |  |  | 2839 |  |  |  |  | T1 | [11 empty] | 1 |  |  | 1.25 |  |  |  | 12.25"
[34 empty] | 1 |  |  | 6.36 |  | 2.812" |  | 12.187"
[34 empty] | 1 |  |  | 10.30 |  | 2.812" |  | 8"
[34 empty] | 1 |  |  | 6.04 |  | 2.812" |  | 12.187"
[34 empty] | 1 |  |  | 30.93 |  | 2.812" |  | 8"
[34 empty] | 1 |  |  | 6.36 |  | 2.812" |  | 12.187
09:30 | [33 empty] | 13 |  |  | 399.31 |  | 2.812" |  | 8"
[34 empty] | 1 |  |  | 31.82 |  | 2.812" |  | 8"
[34 empty] | 2 |  |  | 61.94 |  | 2.812" |  | 8"
[34 empty] | 1 |  |  | 3.77 |  | 2.812" |  | 8"
| 00:00 | 06:00 | [31 empty] | 6 |  |  | 185.32 |  | 3" |  | 5"
743.40
| REMARKS | [16 empty] | Current Operations
DRILLING WITH TOP DRIVE
Daily NPT = hrs / Cumulative NPT = 0.24 days
NPT distribution : ENTP (5.75hrs) / Hole problems(hrs) / HALLIBURTON (hrs)/SLB(hrs)
Geology: 2750' - 2839' limestone - Stage: Dembaba @ 2645'
NOTE: the bit N3 used in B1-95/02 has drilled 3001 ft in 85.75 hr
| PLANNED OPERATION: |  |  |  | DRILLING 12''1/4 SECTION | [18 empty] | Daily Cost: |  | 76291.675
[24 empty] | Cumulative cost: |  | 2599640.145 |  |  | US$ | [7 empty] | Drilling engineer:
A.ALTUMI : (11)
[15 empty] | Planned Day : | [21 empty] | Geologist:
[15 empty] | Actual Day : | [5 empty] | 17 | [15 empty] | Azouz: (17) // Daw: (11)
Superintendent:
Latreche:(13)

## Daily Cost
DETAIL OF CONTRACT SERVICES/EQUIPMENT PROVIDED | Lump Sum - Day Rate | Unit | DISCOUNT
|  |  |  | Qty | daily cost
DRILLING RIG - ENTP
Operating Rate | 1479.16 | $ |  | 22.5 | 33281.1
Stand-by Rate | 1331.25 | $ |  | 1.5 | 1996.875
Reduced Performance Rate | 961.45 | $ |  |  | 0
Force Majeur Rate | 887.5 | $ |  |  | 0
Stacked Rate |  |  |  | 24
ADDITIONAL SERVICES
Additional Catering (> 12 persons ) | 60 | DR | x person | 15 | 900
TOTAL RIG DAYRATE |  |  |  |  | 36177.975
MUD LOGGING - WEATHERFORD
Daily Operating Rate | 1664.7 | $ |  | 1 | 1664.7
Daily Stand by Rate | 200 | $ |  |  | 0
Mobilization unit MUD LOGGING
TOTAL COST MUD LOGGING |  |  |  |  | 1664.7
DOWNHOLE RENTAL TOOLS - WEATHERFORD
Drilling Jar 8” OD X 3” ID Lump Sum Charge | 3510.25 | $ |  |  | 0
|  | $ |  |  | 0
TOTAL COST DOWNHOLE RENTAL TOOLS |  |  |  |  | 0
DRILLING MUD - NOS
Service Cost = senior mud eng. + mud eng. + mud lab =320+270+70= | 660 | $ |  | 1 | 660
Product cost | 18789 | $ |  | 1 | 18789
Mud lab transportation |  | $
TOTAL COST- DRILLING MUD |  |  |  |  | 19449
SOLID CONTROL - NOS
operators service cost | 270 | $ |  | 1 | 270
centrifuge operating | 300 | $ |  | 1 | 300
centrifuge stand by | 150 | $ |  |  | 0
TOTAL COST SOLID CONTROL |  |  |  |  | 570
TOTAL COST- DRILLING MUD & SOLID CONTROL |  |  |  |  | 20019
WELL HEAD MSP DRILEX
Csg Head Housing 13"5/8*3000 SliponLock MSP/DRILEX | 8063 | $ |  | 1 | 8063
|  | $ |  |  | 0
|  | $ |  |  | 0
TOTAL COST ELECTRIC LOGGING SERVICES |  |  |  |  | 8063
COMMUNICATION AND DATA
VSAT rental | 120 | $ |  | 1 | 120
TOTAL COST BITS |  |  |  |  | 120
CASING
74 JOINTS 13"3/8 Casing 61# J55 BTC ( 838.36 m). | 176 | $ |  |  | 0
Casing Transport | 15815.38 | $ |  |  | 0
TOTAL COST CASING |  |  |  |  | 0
CASING ACCESSORIES - WEATHERFORD
13"3/8 Casing Float Shoe & Float Collar | 4167 | $ |  |  | 0
13"3/8 Top & Bottom Plug | 1875 | $ |  |  | 0
13"3/8 Stop Collar & Centralizer | 3972.3 | $ |  |  | 0
Tube Thread Lock & Lube Seal | 468 | $ |  |  | 0
TOTAL COST ACCESSORIES CASING |  |  |  |  | 0
RUNNING CASING AND TUBING - WEATHERFORD
Service run casing 13"3/8 | 7532 | $ |  |  | 0
Crew & Equipment Mob/Demob | 4656 | $ |  |  | 0
TOTAL COST RUNNING CASING & TUBING |  |  |  |  | 0
logging
Logging Unit Stand by | 2500 | $ |  | 0 | 0
GR-RESISTIVITY-CALIPER | 37462.68 | $ |  |  | 0
TOTAL COST ELECTRIC LOGGING SERVICES |  |  |  |  | 0
CEMENTING CASING AND TUBING TESTING & COMPLETION - SCHLUMBERGER
Pers & cmt eqpt daily rate std by while operating | 1270 | $ |  | 1 | 1270
Cementing csg 13"3/8 Products | 42627.64 | $ |  |  | 0
0
0
TOTAL COST CEMENTING CASING & TUBING |  |  |  |  | 1270
RIG SUPERVISION
Drilling Supervision | 3500 | $ |  | 1 | 3500
TOTAL COST RIG SUPERVISION |  |  |  |  | 3500
WATER SUPPLIED WITH OLD DISTANCE & OLD COST SINCE SEPT/02 TO SEPT 14 /2013 -MARAR
0
TOTAL COST OF WATER |  |  |  |  | 0
WATER SUPPLIED WITH NEW DISTANCE AND NEW COST - MARAR
Water truck for camp 20 m3 | 2 | $ | 400 | 1 | 800
Water truck for Rig 20 m3 | 1.54 | $ | 400 | 3 | 1848
TOTAL COST WATER SUPPLIED BASED ON NEW DISTANCE AND NEW COST |  |  |  |  | 2648
WATER SERVICES - NAZAR
Provide package for water well 1 + water well 2 on stand by ( 1200+269 ) | 1469 | $ |  | 1 | 1469
TOTAL COST WATER SERVICES |  |  |  |  | 1469
SECURITY
Watch man | 80 | $ |  | 12 | 960
Equipement | 400 | $ |  | 1 | 400
TOTAL COST SECURITY |  |  |  |  | 1360
Daily cost |  |  |  |  | 76291.675
Note on G2: rep0234: Rig Camp moved 20th August Main Camp, Rig Site Camp and Watchmen Camp operative 24th…Rig move will begin 25th.