## FR
[16 empty] | A | [49 empty] | Date: 09/23/2013
[28 empty] | DAILY DRILLING REPPORT | [18 empty] | N°: |  |  | 10
[5 empty] | Depth @ 24h : |  |  |  | 1974 |  | ft /TVD: |  |  | 1974 |  |  | ft | PROGRESS : | [7 empty] | ft | in |  |  |  | h | [9 empty] | Last Casing/ Liner : | [7 empty] | 20" |  |  |  | 94# J55 BTC | [7 empty] | AT: |  | 304 |  |  |  | ft, | Top AT: |  |  |  | ft
| N° | C | R |  |  | BIT |  | TYPE |  | SERIAL | NOZZELES | [9 empty] | TFA |  | HSI |  |  | WOB(T) |  |  |  | RPM |  |  |  |  | Flow (gpm) |  | Pressure (psi) |  |  |  | Progress (ft) |  |  | Hrs (h) |  | Cumulative | [8 empty] | IADC DULL GRADING | [12 empty] | DEVIATION
|  |  | N° |  |  | SIZE | [14 empty] | (in²) |  | hp/in² |  |  | Min |  | Max |  | Min |  |  | Max | [12 empty] | (ft) |  |  |  |  | (h) |  |  |  | 1 |  | 2 |  | 3 | 4 | 5 |  | 6 |  | 7 | 8 |  | Depth |  | incl |  | Azim. |  | TVD
| 02 | U | 04 |  |  | 16" |  | HR14JMRSV |  | 1299883 | 18 | 18 | 18 |  | 16 | [5 empty] | 0.94 | [24 empty] | 1668 |  |  |  |  | 69.75 |  |  |  | 3 |  | 4 |  | NO | A | E |  | I |  | NO | FM |  | 306 |  | 1
| MUD TYPE: |  | NC FLO | [16 empty] | WEIGHT: |  |  |  | 8.6 | [7 empty] | MUD CLEANER SERVICE = Hours | [35 empty] | PITS |  |  |  | Volumes (bbl)
| F.API: | 11 |  | FUNNEL: |  |  |  | 51 | Y.Point: |  | 28 |  | App. Vis: | [5 empty] | PV: |  | 9 |  |  | F.HPHT: | [21 empty] | Shakers: | [12 empty] | Lost Circ: | [8 empty] | Active |  |  |  | 650
| PH: | 9 |  | GEL 10'': |  |  |  | 11 | GEL 10': |  | 13 |  | M.BT. PPB: 12.5 | [5 empty] | %KCL: |  | 3 |  |  | %W: | [7 empty] | CENTRIFUGE SERVICE | [13 empty] | Mud Cleaner: | [12 empty] | Behind Csg: | [8 empty] | Reserve |  |  |  | 620
[32 empty] | N° |  | Model | [5 empty] | Hours | [5 empty] | S.C.E. Losses | [12 empty] | Other (Hole): | [8 empty] | Kill Mud
| Pf: |  |  | Cacl2: |  |  |  |  | %Solids: |  |  |  | %Sand: | [5 empty] | Ca++: |  | 80 |  |  | NaCI |  |  |  | 0 g/l |  |  |  | 1 |  | BRAND | [11 empty] | Tripping: | [12 empty] | Lost Hole: |  |  |  |  | 75 |  |  |  | Hole |  |  |  | 523
[32 empty] | 2 |  | BRAND | [11 empty] | Encapsulation:
| MF: |  |  | CL- g/l : |  |  |  | 15 | %LGS: |  |  |  | %HGS: | [5 empty] | E-Lime: |  |  |  |  | Cake : |  |  |  | 1 | [17 empty] | Lost Surf: | [7 empty] | 10 |  |  |  |  | Dumped:
| TIMING |  | OPERATION DESCRIPTION | [18 empty] | CODE |  |  | Initial Depth (ft) |  |  |  | Final Depth (ft) |  |  |  |  | Company |  |  | Rate |  | MUD PRODUCTS | [5 empty] | USED |  |  | STORED |  |  |  | UNIT |  |  | Down hole eqts | [6 empty] | SERIAL | [7 empty] | HOURS
| 00:00 | 01:00 | Cont circulation to clean hole - full return Q=130 gpm P= 260 psi | [18 empty] | CIRC |  |  | 1598 |  |  |  | 1598 |  |  |  |  | ENTP |  |  | T1 |  | NC-Bent | [8 empty] | 8 |  |  |  | 1000kg |  |  | Jar
| 01:00 | 01:30 | POOH drill string freely | [18 empty] | RGDD |  |  | 1598 |  |  |  | 1134 |  |  |  |  | ENTP |  |  | T1 |  | Caustic soda | [8 empty] | 73 |  |  |  | 25kg |  |  | Monel | [6 empty] | 1762-5051 | [7 empty] | 64.75
| 01:30 | 04:00 | Back reaming with out return WS=62 T RPM=70 Q=60 gpm P=100 psi | [18 empty] | RGDD |  |  | 1134 |  |  |  | 1108 |  |  |  |  | ENTP |  |  | T1 |  | NUT PLUG (MEDIUM) | [8 empty] | 40 |  |  |  | 25kg |  |  | Shock Tool | [6 empty] | WST-015L | [7 empty] | 111.25
| 04:00 | 04:30 | Cont back reaming with return 50 gpm | [18 empty] | RGDD |  |  | 1108 |  |  |  | 1037 |  |  |  |  | ENTP |  |  | T1 |  | LIME | [8 empty] | 76 |  |  |  | 25kg |  |  | BHA Components
| 04:30 | 15:30 | Cont back reaming with out return (Hard and repetitive back reaming) | [18 empty] | RGDD |  |  | 1037 |  |  |  | 300 |  |  |  |  | ENTP |  |  | T1 |  | SODA ASH | [8 empty] | 41 |  |  |  | 25kg
| 15:30 | 16:15 | Circulation with return (no losses) | [18 empty] | CIRC | [11 empty] | ENTP |  |  | T1 |  | NC - LOSE | [8 empty] | 80 |  |  |  | 25kg |  |  | BHAN° |  |  | Item | [8 empty] | Jts |  | Len (ft) |  | I.D (in) |  | O.D (in)
| 16:15 | 17:00 | POOH drill string In cased Hole | [18 empty] | RGDC |  |  | 300 |  |  |  | 00 |  |  |  |  | ENTP |  |  | T1 |  | PHP A L | [8 empty] | 22 |  |  |  | 5gal |  |  | 4 |  |  | BIT | [8 empty] | 1 |  | 1.41 |  |  |  | 16"
| 17:00 | 18:00 | Bit Service & Clean RB & STB R1 | [18 empty] | SOUT | [11 empty] | ENTP |  |  | T2 |  | NUT PLUG (FINE) | [8 empty] | 40 |  |  |  | 25kg |  |  | 4 |  |  | BIT SUB | [8 empty] | 1 |  | 3.28 |  | 3" |  | 9 1/2"
| 18:00 | 18:45 | Pick up same Bit & RIH Drill String in cased Hole | [18 empty] | DGDC |  |  | 00 |  |  |  | 300 |  |  |  |  | ENTP |  |  | T1 |  | NC PAC UL | [8 empty] | 160 |  |  |  | 25kg |  |  | 4 |  |  | SHOCK/SUB | [8 empty] | 1 |  | 16.07 |  | 3" |  | 9 1/2"
| 18:45 | 21:45 | RIH Drill String in Open Hole With washing f/ 854 T/945 | [18 empty] | DGDD |  |  | 300 |  |  |  | 1727 |  |  |  |  | ENTP |  |  | T1 |  | Kwic SEAL(COARSE) | [12 empty] | 40lb |  |  | 4 |  |  | S/DC | [8 empty] | 1 |  | 9.84 |  | 3" |  | 9 1/2"
| 21:45 | 22:15 | Washing down (Tag @ 1747') | [18 empty] | REFO |  |  | 1727 |  |  |  | 1789 |  |  |  |  | ENTP |  |  | T1 |  | INHABI L | [8 empty] | 24 |  |  |  | 55gal |  |  | 4 |  |  | STB | [9 empty] | 1 | 8.07 |  | 3" |  | 16"
| 22:15 | 22:45 | Top Drive Service | [30 empty] | ENTP |  |  | T1 |  | Clay Sure | [5 empty] | 3 |  |  | 70 |  |  |  | 55gal |  |  |  | 4 |  | DC | [8 empty] | 1 |  | 30.51 |  | 3" |  | 9 1/2"
09:30 | 22:45 | 24:00 | Repair on Top Drive ( circulation Q= 215 gpm ) | [18 empty] | REP | [11 empty] | ENTP |  |  | T3 |  | MICA(FINE) | [8 empty] | 140 |  |  |  | 25kg |  |  | 4 |  |  | STB | [8 empty] | 1 |  | 7.74 |  | 3: |  | 16"
[39 empty] | MICA(MEDIUM) | [8 empty] | 40 |  |  |  | 25kg |  |  | 4 |  |  | DC | [8 empty] | 1 |  | 30.74 |  | 3" |  | 9 1/2"
[39 empty] | XAN-D | [8 empty] | 64 |  |  |  | 25kg |  |  | 4 |  |  | XO | [8 empty] | 1 |  | 3.81 |  | 3" |  | 9 1/2"
|  |  | AFTER MIDNIGHT | [35 empty] | NC - COR S | [12 empty] | 15lb |  |  | 4 |  |  | DC | [8 empty] | 12 |  | 368.74 |  | 2.0812" |  | 8"
| 00:00 | 03:00 | Cont repair on Top Drive ( circulation Q= 215 gpm ) | [35 empty] | NUT PLUG (COARSE) | [12 empty] | 25kg |  |  | 4 |  |  | D Jar | [8 empty] | 1 |  | 31.82 |  | 2.0812" |  | 8"
| 03:00 | 05:30 | Cont RIH drill string in open hole with washing down f/1789' t/1974' | [35 empty] | Kwic SEAL(FINE) | [8 empty] | 60 |  |  |  | 40Ib |  |  | 4 |  |  | DC | [8 empty] | 2 |  | 61.94 |  | 2.0812" |  | 8"
|  |  | ( Q= 520 gpm P= 615 psi RPM= 70 ), with addng deseal in mud | [35 empty] | Kwic SEAL(MEDIUM) | [8 empty] | 90 |  |  |  | 40lb |  |  | 4 |  |  | XO | [8 empty] | 1 |  | 3.77 |  | 2.0812" |  | 8"
| 05:30 | 06:00 | Circulation to clean hole ( Q=586 gpm RPM= 50 P= 820 psi ) | [35 empty] | MICA(COARSE) | [5 empty] | 40 |  |  | 80 |  |  |  | 25kg |  |  | 4 |  |  | HWDP | [8 empty] | 6 |  | 158.23 |  | 3" |  | 5"
[39 empty] | POT.CHLORIDE | [8 empty] | 12 |  |  |  | 1000kg | [5 empty] | Total length(ft) | [8 empty] | 763.06
[39 empty] | RIG WATER | [5 empty] | 1000 | [6 empty] | m3
| REMARKS | [28 empty] | Current Operations | [10 empty] | PUMPS
| DRILLING WITH TOP DRIVE | [39 empty] | PUMP |  |  | OPER |  | SPM |  |  |  | SPP (psi)
| Daily NPT = 0 hrs / Cumulative NPT = days | [39 empty] | P1 |  |  | SCR
| NPT distribution : ENTP (hrs) / Hole problems(hrs) / HALLIBURTON (hrs)/SLB(hrs) | [39 empty] | P1 |  |  | SCR
[41 empty] | P2 |  |  | SCR
| Geology: | [39 empty] | P2 |  |  | SCR
| Stage : Teguentourine @ 1928 ft | [28 empty] | LITHOLOGY - ROP ft/hr
[30 empty] | From ft |  |  |  |  | To ft |  |  | Total Int ft |  |  |  | wc |  | woc |  |  | Stage
NOTE: the bit N2 used in B1-95/02 has drilled 2262 ft in 167 hr | [29 empty] | 492 |  |  |  |  | 692 |  |  | 200 |  |  |  | 20.14 |  | 27.35 |  |  | GORRIA
R1: RB & STB were found balled up - very sticky clay, and Two Bit Nozzles were found plugged. | [29 empty] | 692 |  |  |  |  | 773 |  |  | 81 |  |  |  | 20.01 |  | 31.64 |  |  | GIOSH
| R2: Arrived Halliburton Logging Unit and Engineer, Weatherford TPS Crew (03) and Schlumberger mechanic. | [28 empty] | 773 |  |  |  |  | 1385 |  |  | 612 |  |  |  | 26.6 |  | 31.6 |  |  | ABREGHS
| R3: Received 02 Varel PDC Bits 12"1/4 and 04 Varel Rock Bits 16". | [28 empty] | 1385 |  |  |  |  | 1928 |  |  | 543 |  |  |  | 22 |  | 32 |  |  | RAS HAMIA
[30 empty] | 1928 | [16 empty] | TEGUENTOURINE
| PLANNED OPERATION: | [5 empty] | Drilling section 16'' | [19 empty] | Last BOP'S TEST : | [15 empty] | Daily Cost: | [5 empty] | 65791.9925
[27 empty] | Accident Free Days : | [8 empty] | 500 | [6 empty] | Cumulative cost: | [5 empty] | 1822832.4625 | [5 empty] | US$ | [13 empty] | Drilling engineer:
| REQUIREMENTS: | [25 empty] | Last Safety Meeting : | [8 empty] | SEPT/23/2013 | [32 empty] | A.ALTUMI : (03)
[27 empty] | Planned Day : | [41 empty] | Geologist:
[27 empty] | Actual Day : | [8 empty] | 9 | [32 empty] | Azouz: (09) // Daw: (03)
Superintendent:
Latreche:(05)

## Daily Cost
DETAIL OF CONTRACT SERVICES/EQUIPMENT PROVIDED | Lump Sum - Day Rate | Unit | DISCOUNT
|  |  |  | Qty | daily cost
DRILLING RIG - ENTP
Operating Rate | 1479.16 | $ |  | 21.75 | 32171.73
Stand-by Rate | 1331.25 | $ |  | 1 | 1331.25
Reduced Performance Rate | 961.45 | $ |  | 1.25 | 1201.8125
Force Majeur Rate | 887.5 | $ |  |  | 0
Stacked Rate |  |  |  | 24
ADDITIONAL SERVICES
Additional Catering (> 12 persons ) | 60 | DR | x person | 20 | 1200
TOTAL RIG DAYRATE |  |  |  |  | 35904.7925
MUD LOGGING - WEATHERFORD
Daily Operating Rate | 1664.7 | $ |  | 1 | 1664.7
Daily Stand by Rate | 200 | $ |  |  | 0
Mobilization unit MUD LOGGING
TOTAL COST MUD LOGGING |  |  |  |  | 1664.7
DOWNHOLE RENTAL TOOLS - WEATHERFORD
Lump sum use of 9 1/2 SHOCK SUB TO DRILL 26" HOLE SECTION | 3510 | $ |  |  | 0
transport shock sub to the rig site | 5000 |  |  |  | 0
TOTAL COST DOWNHOLE RENTAL TOOLS |  |  |  |  | 0
DRILLING MUD - NOS
Service Cost = senior mud eng. + mud eng. + mud lab =320+270+70= | 660 | $ |  | 1 | 660
Product cost | 723.5 | $ |  | 1 | 723.5
Mud lab transportation |  | $
TOTAL COST- DRILLING MUD |  |  |  |  | 1383.5
SOLID CONTROL - NOS
operators service cost | 270 | $ |  | 1 | 270
centrifuge operating | 300 | $ |  |  | 0
centrifuge stand by | 150 | $ |  | 1 | 150
TOTAL COST SOLID CONTROL |  |  |  |  | 420
TOTAL COST- DRILLING MUD & SOLID CONTROL |  |  |  |  | 1803.5
WELL HEAD MSP DRILEX
0
TUBING HEAD 11".5000x 7 1/16.5000 | 8411 | $ |  |  | 0
XMASTREE 7 1/16.5000x 4 1/16.5000 | 21629 | $ |  |  | 0
Set Bridge Plug @ 5855' | 20279.4 | $ |  |  | 0
GR-CCL (Correlation:13/05/2013) | 27379.2 | $ |  |  | 0
Set Bridge Plug @ 7948' | 29153.76 | $ |  |  | 0
TOTAL COST ELECTRIC LOGGING SERVICES |  |  |  |  | 0
COMMUNICATION AND DATA
VSAT rental | 120 |  |  | 1 | 120
TOTAL COST BITS |  |  |  |  | 120
CASING
7 JOINTS CASING 20" 94 # J55 BTC ( 81.88m ) | 380 | $ |  |  | 0
TOTAL COST CASING |  |  |  |  | 0
CASING ACCESSORIES - WEATHERFORD
20" FLOAT SHOE | 3569 | $ |  |  | 0
TUBE THREAD LOCK | 90 | $ |  |  | 0
TRANSPORTATION COST F/103A weatherford base T/ SIPEX Rig site | 5000 | $ |  |  | 0
TOTAL COST ACCESSORIES CASING |  |  |  |  | 0
RUNNING CASING AND TUBING - WEATHERFORD
CREW & EQUIPMENT MOB/DEMOB | 4656 | $ |  |  | 0
SERVICE RUN CSG 20" | 8546 | $ |  |  | 0
TOTAL COST RUNNING CASING & TUBING |  |  |  |  | 0
CEMENTING CASING AND TUBING TESTING & COMPLETION - SCHLUMBERGER
Pers & cmt eqpt daily rate std by while operating | 1270 | $ |  | 1 | 1270
CEMENTING COST 20" CASING | 7972.2 | $ |  |  | 0
TOTAL COST CEMENTING CASING & TUBING |  |  |  |  | 1270
logging |  |  |  |  | 0
0
Logging Unit Stand by | 2500 |  |  |  | 2500
0
TOTAL COST ELECTRIC LOGGING SERVICES |  |  |  |  | 2500
RIG SUPERVISION
Drilling Supervision | 3500 | $ |  | 1 | 3500
TOTAL COST RIG SUPERVISION |  |  |  |  | 3500
WATER SUPPLIED WITH OLD DISTANCE & OLD COST SINCE SEPT/02 TO SEPT 14 /2013 -MARAR
0
0
0
0
TOTAL COST OF WATER |  |  |  |  | 0
WATER SUPPLIED WITH NEW DISTANCE AND NEW COST - MARAR
Water truck for camp 20 m3 | 2 | $ | 400 | 1 | 800
Water truck for Rig 20 m3 | 1.54 | $ | 400 | 25 | 15400
TOTAL COST WATER SUPPLIED BASED ON NEW DISTANCE AND NEW COST |  |  |  |  | 16200
WATER SERVICES - NAZAR
Provide package for water well 1 + water well 2 on stand by ( 1200+269 ) | 1469 | $ |  | 1 | 1469
TOTAL COST WATER SERVICES |  |  |  |  | 1469
SECURITY
Watch man | 80 | $ |  | 12 | 960
Equipement | 400 | $ |  | 1 | 400
TOTAL COST SECURITY |  |  |  |  | 1360
Daily cost |  |  |  |  | 65791.9925
Note on G2: rep0234: Rig Camp moved 20th August Main Camp, Rig Site Camp and Watchmen Camp operative 24th…Rig move will begin 25th.